# Project Charter Template

| PROJECT NAME |  | PROJECT MANAGERS | Team Name |
| --- | --- | --- | --- |
| A Data-Driven Analysis of the Global Aging Population and the Rising Burden of Age-Related Diseases |  | Vishal Sharma | Global Health Analytics Group (Group 7) |

PROJECT OVERVIEW

| PROBLEM OR ISSUE | With the increasing elderly population, there is a parallel rise in chronic and neurodegenerative conditions. However, there remains a lack of integrated data analysis to identify the root causes and predictors of these diseases. Existing research often focuses on specific regions or diseases without comprehensive global data integration. This project seeks to analyze global aging and healthcare datasets to: - Detect key patterns and correlations among demographic, lifestyle, and medical variables. - Identify risk factors and predictors for Alzheimer’s and related diseases. - Develop predictive models to aid in early detection and resource allocation. |
| --- | --- |
| PURPOSE OF PROJECT | The global population aged 60 years and above is increasing rapidly due to medical advancements, improved living standards, and declining fertility rates. While this demographic shift reflects social progress, it also presents challenges — particularly the rising prevalence of chronic and neurodegenerative diseases such as Alzheimer’s, dementia, Parkinson’s disease, and cardiovascular disorders. These diseases affect quality of life, healthcare expenditure, and dependency ratios. Leveraging data analytics and predictive modeling can help identify early risk factors, optimize healthcare resources, and guide public health policies for elderly care. This project applies data analytics techniques to examine global datasets on aging populations and age-related diseases to uncover patterns, predictors, and actionable insights for improving healthcare outcomes and resource planning. |
| BUSINESS CASE | Aging populations will significantly influence healthcare expenditure and public policy worldwide. By analyzing cross-national datasets, this project can provide data-driven insights that inform: - Early detection of Alzheimer’s and related diseases, reducing future treatment costs. - Evidence-based resource allocation for elderly care. - Strategic planning for governments and healthcare institutions. The project supports sustainable healthcare management through predictive analytics and can guide policymakers in improving preventive programs and medical support systems for senior citizens. |
| GOALS / METRICS | To conduct a comprehensive data-driven analysis of the aging population and identify trends, risk factors, and predictive indicators associated with age-related diseases, with a focus on Alzheimer’s disease. |
| EXPECTED DELIVERABLES | - Demographic Analysis: Examine aging population trends by gender, region, and socioeconomic factors. - Disease Correlation: Explore relationships between health indicators and disease prevalence among the elderly. - Predictive Modeling: Develop models to predict the likelihood of Alzheimer’s and related diseases. - Risk Factor Identification: Highlight significant health, lifestyle, or demographic factors contributing to disease progression. - Visualization and Insight Generation: Create dashboards and graphs to communicate findings. - Policy Recommendations: Suggest data-driven solutions to improve elderly healthcare management and preventive strategies. |

PROJECT SCOPE

| WITHIN SCOPE | - Analysis of global datasets (e.g., WHO, Kaggle, and government health repositories). - Focus on populations aged 60+ years. - Use of EDA, correlation analysis, and machine learning models. - Disease focus: Alzheimer’s, dementia, Parkinson’s, and other chronic conditions. |
| --- | --- |
| OUTSIDE OF SCOPE | - Individual-level clinical trials or longitudinal patient tracking. - Real-time health monitoring implementations. |

TENTATIVE SCHEDULE

| KEY MILESTONE | START | FINISH |
| --- | --- | --- |
| Form Project Team / Preliminary Review / Scope | September 5, 2025 | September 15, 2025 |
| Finalize Project Plan / Charter / Kick Off | September 16, 2025 | September 30, 2025 |
| Data Collection & Literature Review | October 1, 2025 | October 20, 2025 |
| Data Cleaning & Exploratory Analysis | October 21, 2025 | November 15, 2025 |
| Predictive Modeling & Visualization | November 16, 2025 | December 5, 2025 |

RESOURCES

| PROJECT TEAM | The project team consists of five members with complementary expertise in data analytics, research, engineering, and visualization. Each member contributes specific skills necessary for the project’s success: - Vishal Sharma (Data Research Lead): Responsible for data collection, cleaning, preprocessing, and ensuring dataset reliability. - Harjeet Kaur (Literature & Analysis Specialist): Handles academic research, literature review, and identification of key analytical trends. - Om Patel (Data Engineer): Manages data sourcing, integration from multiple repositories (WHO, Kaggle, etc.), and technical preprocessing. - Kirti Sharma (Analytics & Visualization Lead): Develops predictive models, performs advanced analytics, and designs visual dashboards. - Krupa Patel (Documentation & Reporting Lead): Prepares project documentation, manages coordination, and creates final reports and presentations. |
| --- | --- |
| SUPPORT RESOURCES | - Computing Infrastructure: Access to high-performance college lab computers, Google Colab Pro, and Python-based environments for analysis and modeling. - Software Tools: Python (NumPy, Pandas, Scikit-learn, Matplotlib, Seaborn), Power BI for dashboards, and Excel for preliminary data review. - Data Sources: - World Health Organization (WHO) Open Data Repository - Kaggle datasets on aging, healthcare, and Alzheimer’s disease - World Bank and OECD demographic databases - Institutional Support: - Guidance and supervision by Professor Manajeri Maheshwari - Access to St. Clair College’s research and analytics lab facilities - Academic library resources for literature and journal access - Collaboration Tools: Google Drive and GitHub for shared data storage, version control, and report integration. Microsoft Teams for meetings, discussion, and progress tracking. |
| SPECIAL NEEDS | - Reliable internet access for data retrieval and cloud computation. - Access to datasets exceeding 100 MB (requires cloud storage). - Occasional GPU access for training machine learning models via Colab Pro. - Institutional approval for using external open-source health datasets. |

COSTS

| COST TYPE | VENDOR / LABOR NAMES | RATE | QTY | AMOUNT |
| --- | --- | --- | --- | --- |
| Labor (Team Contribution) | 5 Data Analysts / Researchers | $25 per hour (student consulting rate) | 5 members × 80 hours each | $10,000 |
| Software / Tools | Google Colab Pro | $15 / month | 4 months | $60 |
|  | Microsoft Excel / Power BI Pro | $13.70 / month | 4 months | $55 |
|  | Jupyter Notebook / VS Code Add-ons | $10 flat (extensions) | 1 | $10 |
| Data Sources / Licenses | WHO, CIHI, StatCan (data access, API usage, downloads) | $100 one-time fee | 1 | $100 |
| Visualization / Dashboard Tools | Tableau Student License (if paid version considered) | $20 / month | 4 months | $80 |
| Cloud Storage & Collaboration | Google Drive (200 GB Plan) | $2.79 / month | 4 months | $12 |

| Printing & Presentation Materials | Local Print Shop | $0.25 / page | 40 pages | $10 |
| --- | --- | --- | --- | --- |
| Hardware / Equipment | Laptop depreciation cost | $30 / month | 4 months | $120 |
| Miscellaneous Expenses | Team meetings, snacks, transit, contingency | Estimated | - | $40 |
|  |  |  | TOTAL | $10,487 CAD |

| TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT |
| --- | --- | --- | --- | --- | --- |
| Specific Cost Savings | Improved forecasting reduces unnecessary healthcare spending and hospital resource waste. |  |  |  | $8,000+ per year) |
| Higher Productivity (Soft) | Automating data cleaning, analysis, and dashboard creation reduces manual processing time for analysts. |  |  |  | Equivalent to 40–60 hours saved per analyst |
| Better Decision Making | Predictive modeling for Alzheimer’s, dementia, and age-related diseases helps policymakers plan budgets and intervention strategies. |  |  |  | High impact |
| Improved Compliance | Use of validated WHO datasets strengthens public-health reporting standards and ensures accuracy. |  |  |  | High |
| Risk Reduction | Early forecasting reduces emergency surges, hospital overcrowding, and last-minute staffing costs |  |  |  | $3,000+ avoided risk costs |
| Less Maintenance | Automated pipelines reduce repetitive manual work; dashboards update with minimal effort. |  |  |  | Approx. $1,500 efficiency gain |
| Other Costs Avoided | Predictive health analytics helps prioritize preventive care → reduces long-term treatment costs. |  |  |  | $2,000 savings estimate |
|  |  |  | TOTAL BENEFIT |  | $15,000+ CAD |

Financial Summary / Business Case

| Payback Period, NPV Analysis | Not applicable – academic research project. |
| --- | --- |
| Non-financial Considerations | Improved public awareness of aging trends, better policy planning for elderly healthcare. |

RISKS, CONSTRAINTS, AND ASSUMPTIONS

| RISKS | - Limited or incomplete global data availability. - Potential bias in regional datasets. - Model accuracy affected by data imbalance. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| CONSTRAINTS | - Time limitations within academic semester. - Restricted access to premium health data sources. - Team coordination across multiple tasks |  |  |  |  |  |
| ASSUMPTIONS | - Datasets used are authentic and publicly available. - Members have adequate technical skills in Python and analytics tools. - Institutional support for presentation and computing resources. |  |  |  |  |  |
| PREPARED BY |  | TITLE |  |  |  | DATE |
| Vishal Sharma Om Patel Krupa Patel Kirti Sharma Harjeet Kaur |  | Data Research Lead – Global Health Analytics Project (Group 7) |  |  |  |  |